## Instructions_WorkPlan_En (hidden)
Costed Work Plan for CCM Funding Agreements
- As part of the CCM Funding Agreement, the Costed Work Plan is a legal document that supports the disbursements to cover the CCM Activities and CCM Secretariat costs financed by the Global Fund, as per the CCM Guidelines.
- The CCM Secretariat should always keep the track and documentation on the estimation of costs presented in this Costed Work Plan.
- The information reflected in this document will serve to track the execution of activities and the detailed budget that will be kept by the CCM for accountability purpose, LFA verification and Audits.
- The Costed Work Plan contains 4 sections 1. General Information 2. Fixed costs and HR positions covered by the CCM Funding Agreement 3. CCM Activities 4. Co-funding
- In general, only the yellow cells can be filled in free format. Some drop-downs (cells in grey) and formulas are part of the document, we request to please not modify them, in order to obtain a standardized document across all the CCMs financed by the Global Fund.
-The Section 1 "General information" reflects the basic information about the CCM Funding Agreement
- At the top of the document the table "Grand Total" shows the final amount to be covered by the CCM Funding Agreement. It coincides with the corresponding year amount highlighted in the Facesheet.
The Section 2 "Fixed costs and HR positions covered by CCM Funding Agreement" includes any CCM Secretariat recurrent cost. This category containes 2 separated tables to summarize the fixed costs, making sure the categories are grouped so that there is one "Cost Grouping" per line, and the costs related to the Human Resources.
- The Section 3 "CCM Activities" shows the planning of activities throughout the year, and the corresponding budget. The list of activities is standard for all the CCMs, any detailed or specific name that could refer to the CCM budget can be added in the assumptions or comments column.
- Inside the table of the Section 3, the column "Total No of Activities" must quantify the number of activities planned for the year as per the information filled in the columns "M1…M12". The column "Budget" shows the total cost for the line in the agreed currency (US$/EUR) for the CCM Funding.
- The Columns "Costs Grouping" and "Performance Area" respond to the approved terms by the Global Fund.
- The table of the section 4 "Co-funding" is mandatory only if the 3-year budget is above USD 300,000. However, all the CCMs invited to include the total financial needs for an ideal functionning of the CCM.
- Please refer to the Spreadsheet "Definitions" for a detailed description of all the Cost Groupings and the Performance Areas used in this Costed WorPlank.
- Please refer to the Spreadsheet "Lists" for a complete overview of all the category options you can use to fill this Costed Work Plan.
Version November 2019

## Instructions_WorkPlan_Fr (hidden)
Plan de travail chiffré pour les Accords de financement des CCM
-Dans le cadre de l'Accord de financement du CCM, le plan de travail chiffré est un document juridique qui soutient les décaissements pour couvrir les coûts des activités du CCM et du Secrétariat du CCM financés par le Fonds mondial, conformément aux Lignes directrices du CCM.
- Le Secrétariat du CCM doit toujours conserver la trace et la documentation sur l'estimation des coûts présentée dans ce plan de travail chiffré.
- L'information contenue dans ce document servira à suivre l'exécution des activités et le budget détaillé qui seront conservés par le CCM à des fins de responsabilité, de vérification de l'ALF et d'audit.
- Le plan de travail chiffré est composé de 4 sections: 1. Information générale 2. Coûts fixes et les postes de RH couverts par l'accord de financement du CCM 3. Activités du CCM 4. Co-financement
- En général, seules les cellules jaunes peuvent être remplies en format libre. Certaines listes déroulantes (cellules en gris) et les formules font partie du document, nous vous demandons de ne pas les modifier, et ce afin d'obtenir un document standardisé pour tous les CCM financés par le Fonds mondial.
-La section 1 "General Information" ("Information générale") reflète les informations de base de l'Accord de financement du CCM
- En haut du document, le tableau "Grand Total" indique le montant final couvert par l'Accord de financement du CCM. Il coïncide avec le montant de l'année correspondante surligné dans la Facesheet.
- La section 2 "Fixed costs and HR positions covered by CCM Funding Agreement" ("Frais fixes et postes de RH couverts par l'Accord de financement du CCM") comprend tout coût récurrent du Secrétariat du CCM. Cette catégorie contient 2 tableaux séparées pour résumer les coûts fixes, en s'assurant que les catégories sont regroupées de sorte qu'il y ait un "groupement des coûts" ("Cost Grouping") par ligne et les coûts liés aux ressources humaines.
- La section 3 "CCM Activities" ("Activités du CCM") montre la planification des activités tout au long de l'année et le budget correspondant. La liste des activités est standard pour tous les CCM, tout nom détaillé ou spécifique qui pourrait se référer au budget du CCM peut être ajouté dans la colonne des hypothèses ou des commentaires.
- Dans le tableau de la section 3, la colonne "Total of activities" ("Nombre total d'activités") doit quantifier le nombre d'activités prévues pour l'année selon les informations remplies dans les colonnes "M1 ... M12". La colonne " Budget" indique le coût total de la ligne dans la devise convenue (US $ / EUR) pour le financement du CCM.
- Les Colonnes "Cost Grouping" ("Groupement de coûts") et "Performance Area" ("Zone de performance") répondent aux termes approuvés par le Fonds mondial.
- Le tableau de la section 4 "Co-financing" ("Co-financement") est obligatoire uniquement si le budget pour 3 ans est supérieur à USD 300,000. Cependant, tous les CCM ont été invités à inclure les besoins financiers totaux pour un fonctionnement idéal.
- La section 5 "Special Conditions" ("Conditions spéciales") résume l'état des conditions spéciales énoncées dans l'Accord de financement du CCM.
- Veuillez vous référer à la feuille de calcul "Definitions" (disponible uniquement en anglais) pour une description détaillée de tous les groupements de coûts et des zones de performance utilisées dans ce plan de travail chiffré.
- Veuillez consulter la feuille de calcul "Lists" (liste disponible uniquement en anglais) pour un aperçu complet de toutes les options de catégorie que vous pouvez utiliser pour remplir ce plan de travail chiffré.
Version Novembre 2019

## Instrucciones_WorkPlan_Es
Plan de trabajo costeado para los Acuerdos de financiamiento de los MCP
- Como parte del Acuerdo de Financiación del MCP, el Plan de trabajo costeado es un documento legal que apoya los desembolsos para cubrir los costos de las actividades del MCP y de la Secretaría del MCP financiados por el Fondo Mundial, de acuerdo con las Directrices del MCP.
- La Secretaría del MCP debe guardar siempre un registro y la documentación sobre la estimación de costos presentada en este Plan de trabajo costeado.
- La información reflejada en este documento servirá para rastrear la ejecución de las actividades y el presupuesto detallado que mantendrá el MCP para fines de rendición de cuentas, verificación del ALF y Auditorías.
- El Plan de trabajo costeado tiene 4 secciones: 1. Información general 2. Costos fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP 3. Actividades del MCP 4. Contrapartida
- En general, sólo las celdas amarillas se pueden rellenar en formato libre. Algunos desplegables (celdas en gris) y fórmulas forman parte del documento, solicitamos no modificarlos, a fin de obtener un documento estandarizado para todos los MCPs financiados por el Fondo Mundial.
-La Sección 1 "General Information" ("Información general") refleja la información básica sobre el Acuerdo de financiamiento del MCP
- En la parte superior del documento, el cuadro "Grand Total" muestra el monto final que será cubierto por el Acuerdo de financiamiento del MCP. Coincide con la cantidad del año correspondiente resaltada en la Facesheet.
- La Sección 2 "Fixed costs and HR positions covered by CCM Funding Agreement" ("Costos fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP") incluye cualquier costo recurrente de la Secretaría del MCP. Esta categoría contiene 2 tablas separadas para resumir los costos fijos, asegurándose de que las categorías se agrupan de manera que haya una "Agrupación de Costos" ("Cost Grouping") por línea y los costos relacionados con recursos humanos.
- La Sección 3 "CCM Activities" ("Actividades del MCP") muestra la planificación de las actividades a lo largo del año y el presupuesto correspondiente. La lista de actividades es estándar para todos los MCP, cualquier nombre detallado o específico que pudiera referirse al presupuesto del MCP se puede agregar en la columna de supuestos o comentarios.
- Dentro de la tabla de la Sección 3, la columna "Total No of Activities" ("Número Total de Actividades") debe cuantificar el número de actividades previstas para el año según la información presentada en las columnas "M1 ... M12". La columna "Budget" ("Presupuesto") muestra el costo total de la línea en la moneda acordada (USD/EUR) para el financiamiento del MCP.
- Las columnas "Costs Grouping" ("Agrupación de costos") y "Performance Area" ("Área de desempeño") responden a los términos aprobados por el Fondo Mundial.
- El cuadro de la sección 4 "Co-funding" ("Contraparte") es obligatorio únicamente si el presupuesto a 3 años supera los USD 300.000. Sin embargo, todos los MCPs fueron invitados a incluir las necesidades financieras totales para un funcionamiento ideal del MCP.
- Consulte la pestaña "Definitions" (únicamente disponible en inglés) para obtener una descripción detallada de todas las agrupaciones de costos y las áreas de desempeño utilizadas en este Plan de trabajo costeado.
- Consulte la pestaña "Lists" (únicamente disponible en inglés) para obtener una descripción completa de todas las opciones de categoría que puede utilizar para llenar este Plan de trabajo costeado.
Versión Noviembre 2019

## Definitions
Instructions
A. General instructions
1 | Which worksheets to complete | The CCM funding application requires the CCM to complete the following worksheets: ► Performance framework ► Detailed budget - Period 1 including detailed assumptions ► Detailed budget - Period 2 including detailed assumptions ► Co-Payment ► CCM funding request form
The following forms will be automatically generated: - Work plan - Summary budget per performance area, per Cost Grouping and per source of fund (SOF)
Additionally the CCM may include other worksheets or attachments to provide additional information to support the detailed budget e.g. to support a costing assumption.
2 | Recommended steps in completing the template | ! CAUTION : PLEASE NOTE THAT THIS TEMPLATE CONTAINS MACROS. You should ensure that you have the right setting: On the Menu Bar, Select “Tools”, then move the cursor over “Macro” and select “Security”. From the options select “Medium” and then select “Ok”. Close the file and re-open it. You will receive a security warning. Select “Enable Macros”. This will enable all the features of the Budget Toolkit to be fully active.
3 | Cell formatting | Below the applicant is taken through an explanation of the intended data to be entered in each column of the template. Note that most cells have fixed formatting which should not be adjusted unless absolutely necessary.
6 | Information sources | If applicants have any technical difficulty in using this template or are unsure about any aspect of it, guidance may be obtained from the Global Fund through sending an e-mail to ccm@theglobalfund.org
B. Specific instructions for data entry, by each column header - Menu
| Column header | Instructions | Possible check?
| Menu | ►Region, Country, CCM are to be selected from the drop down lists. ►Enter in the name of the recipient organization. The GF Secretariat will enter the Agreement number.
C. Specific instructions for data entry, by each column header - Performance Framework
| Column header | Instructions | Possible check?
Section A. General information
| Funding start date | ►Enter Day, Month and Year (numeric values) for the intended start of the funding period. Final date will be determined by the Global Fund based on completion of the application review process.
| Year 1 and Year 2 | This section gives information on the reporting periods over the funding term, dates when progress updates and disbursement requests (PUDR) are due. Based on a 12 continuous month periods, the cells will be populated automatically. The reporting periods could be aligned with national reporting cycle. For any change in the proposed format, pls submit your request to the CCM Team. | Progress Update and Disbursement request are due one month upon completion of Q3 and Q7 (month 10 and month 22 respectively).
| Section B. Overall goal and objective | Goal and Objectives are broad and overarching statements of long term outcome of the program and should be consistent with the strategy defined by the CCM during the planning exercise. ►Each strategic objective should be in line with the Performance areas defined by the Global Fund.
| Section C. Performance Framework | Performance Area ►Select a key Performance Area as defined under Section B above. A drop-down list shows the areas applicable to CCM funding. This field cannot be overwritten.
| Section C. Performance Framework | Selection of Indicator(s): ► Indicator #1 ' % of planned oversight activities completed with documented participation by all CCM constituencies' is compulsory. All CCMs applying for expanded funding should provide base line data and set targets (intended results) for this indicator. ► Subsequent indicators are to be selected from the GF core list, in line with the overall objectives defined in Section B above. The CCM Team recommends that the maximum number of indicators for a two year plan is five. ► On exceptional cases, CCMs can propose to measure an indicator outside the GF core list of indicators. Those indicators will have to be reviewed and approved by the CCM Team before the funding request can be finalized by the CCM and submitted to the GF. ► Indicators should be numbered sequentially in the first column of this section. | Information has to be provided in all cells relating to each indicator. The indicator number cell will turn RED when information is missing.
| Section C. Performance Framework | Setting baselines ►baselines must be provided for each of the selected indicator with a clear data source, ideally a reference document. If baselines cannot be given at the onset of the program, they should be established. Setting targets ►targets should be cumulative and set according to when the indicators will be measured. Tied to other donors (Y/N) ►Whether the target reflects solely Global Fund financing through the current grant (Tied Yes - activities are funded solely by the current grant) or co-financed (Not tied when targets are not directly tied to GF financing, when GF resources contribute and thus are shared between all donors involved). Baselines include targets ►In this column you should select 'Yes' or 'No' from the drop down list to indicate whether or not baselines are included in each target. In general, the baseline is to be included. | For baselines, supporting documentation will have to be provided for future verification by the LFA.
D. Specific instructions for data entry, by each column header - Detailed budgets Period 1 and Period 2
As noted above, when a line of data is entered in the "Detailed budget - Year 1" the same Reference Number, objective, Performance Area, activity and Cost Grouping will automatically be repeated on the Year 2 detailed budget sheets ("Detailed budget - Year 2"). Note that it does not mean that each activity line has to be completed with cost data (i.e. with unit cost and quantity data) in each year. If there is no budget data for an activity in a year, you should enter zeros. If you have a NEW activity in "Detailed budget - Year 2" you must enter the activity in "Detailed budget - Year 1" (with zero cost in year 1), so that the activity is automatically copied into the following years.
!Caution: Applicants should not add any totals or sub-totals in any worksheet within the template as this will interfere with the logic of the budget summaries.
Applicants will note that the detailed budget worksheets ("Detailed budget - Year 1" and "Detailed budget Year 2" ) are automatically totaled and analyzed into the summary budget worksheet ("Summary budget, by Cost Grouping, Performance Area and source of fund (SOF)"). This involves the use of pivot tables that have been pre-set to analyze the data input. Applicants should not attempt to adjust these tables as this may corrupt their functioning.
| Column header | Instructions | Possible check?
| Objective Number | This number refers to the objective defined in section B - Overall goals and objectives in the performance framework worksheet and for which a budget activity is to be defined.
| Performance Area | The performance area will be populated automatically based on the information provided in Section B of the performance framework sheet.
| Activity | In the column you should describe clearly and concisely, the planned budget activity. The wording should be consistent with that used in the work plan.
| Directly related indicator | This column has been included to easily show the link between the budget and the Performance Framework. A reference should be entered where the activity matches with a target within the Performance Framework. The number entered should be the indicator number referenced in the Performance Framework. | Cross check from the Performance Framework to see that all directly related budget activities show a reference to the relevant indicator
| Assumptions | This column requires a short description of the detailed assumptions used to arrive at the budget amount and may make cross reference to a detailed document submitted with this request for funding. Budget assumptions should provide sufficient information to be able to determine how unit quantities and unit costs were calculated. | Confirm that the assumptions spelled out comply with the requirement that all key assumptions, including unit costs and quantities should be provided.
| Cost categories | This is a drop down list of 8 defined cost categories. Each budget activity should be associated with a Cost Grouping. For further description of the categories refer to the Definition table. | Check that the allocation follows the Global Fund Cost Grouping descriptions contained in the guidelines. Ensure costs are eligible for GF funding as per the definition and limitations stated in this section of the application form.
| Measurement unit | This is the unit of measurement to which the unit cost (in the next column) refers. It will depend on the nature of the activity and the complexity of the costing method. Examples may include: monthly salary cost per person, cost per meeting, cost of a site visit, etc. Note that costs such as Human Resources showing a simple multiplication of unit cost by quantity may not be appropriate in the template. Applicants should explain the detailed assumptions of Human Resources costs in the worksheet "detailed assumptions" or refer to a separate document. | Ensure clear and concise information is provided for LFA and GF review of the application.
| Unit cost | This is the unit cost of the item described in the preceding column in the currency defined in Section A. General information - Performance Framework worksheet. Budget assumptions should provide sufficient information to be able to determine how unit costs were calculated. If the item is costed in a currency other than the proposed currency, the working to convert the unit cost to the defined currency should be shown in the "Detailed assumptions" worksheet. If there is a differential unit cost for the same activity line in the same quarter then a separate row should be added in the budget, and the calculation explained in the "Detailed assumptions worksheet".
| Quantity | This will be the actual quantity for which the cash budget is required. Note: budget assumptions should provide sufficient information to be able to determine how unit quantities were calculated. | Where the activity has a directly related target in the Performance Framework, ensure the budget is consistent with the Performance Framework.
| Total amount | This cell contains a formula which multiplies the Unit cost by the Quantity by quarter in Years 1 and 2. | No specific checks proposed
| Total quantity Period 1 / Total quantity Period 2 | This is a formula which sums the four quarterly quantities to give the annual quantity. | Where the activity has a directly related target in the Performance Framework, ensure the budget is consistent with the Performance Framework. If there are differences, this should be explained in the "Detailed assumptions" worksheet.
| Total amount Period 1 / Total amount Period 2 | This is a formula which sums the four quarterly budget amounts in the proposal currency to give the annual budget. | Ensure the reported amounts are accurate.
E. Other Sources of funding (SOF)
| Column header | Instructions | Possible check?
CCMs applying for more than USD100,000 per year are required to report in this section the source of funds and amounts mobilized as required under the CCM funding policy.
| Summary funding distribution | Global Fund Amount The cells corresponding to 'GF Funding amount' will be populated automatically based on the information provided in sheets 'detailed budget Year 1' and 'detailed budget Year 2' . | Amounts specified under this section of the report are accurate and supported by clear documentation for future verification.
Source of funds (SOF)1, 2, etc ►For each non GF funding you will specify the funding source and the amount committed for the CCM. ►Under Section 2 of the form (Section 2 Detailed funding information) you will have to specify the percentage of this amount going to ‘Secretariat support Costs’ and the percentage going specifically to support directly CCM performance costs. ►For the amount to support CCM performance costs, you are then required to specify the percentage which is allocated for each performance area (oversight, constituency engagement, alignment, capacity building / gender).
F. CCM funding request form
| Column header | Instructions | Possible check?
Section A: budget summary
| A1 to A7 | Information in this section will be uploaded with data entered in different parts of the form. | Verify information in this section of the report is accurate and matches information entered in other parts of the form (detailed and summary budgets).
Section B: recipient entity information
| B1 | Name of the recipient entity is populated automatically. ►Sector has to be specified.
| B2 to B5 | ►Complete information has to be entered | Ensure all information is complete and accurate.
Section C: CCM approval
|  | ►Name and title information has to be provided for each CCM Member. The funding application is completed only when it has been signed by all members. Original document is to be submitted to the Global Fund Secretariat. | Ensure all information is complete and accurate.
| Others | Others significant costs which do not fall under the above-defined cost group. Costs under this cost group are to be clearly specified.
Definitions
NOTE: The CCM Secretariat should always keep the track and documentation on the estimation of costs and the variation agains the budget.
| Cost grouping | General Description | Limitations
| Human Resources | Salaries, wages and related costs (pensions, incentives, supplements, top ups, and other employee benefits, etc.) relating to all employees (including field personnel), and employee recruitment costs. Eligible costs under this cost grouping are the salaries of CCM Secretariat staff. | (i) Secretariat staff should not exceed 2 persons. (ii) Scope of work for key personnel is to be submitted to the GF CCM Team for approval. (iii) CCM funding shall not be used to remunerate CCM members. (iv) Salaries must be commensurate with national salary scales.
| Travel-related Costs (includes meetings' expenses) | Workshops, meetings, training publications, training-related travel, including training per-diems. Do not include human resources costs related to training which should be included under the Human Resources category. Constituency consultations for non government constituencies only (e.g. civil society) and processes to promote and improve the quality of stakeholder participation, including travel costs for civil society participation. Eligible costs under this group of activities includes (i) CCM general meeting expenses, travel costs for members to attend CCM meetings, CCM support costs. (ii) Expendable equipment, office supplies, travel, field visits and other costs relating to program planning and administration. Legal, accounting costs, bank charges, etc. | (i) Ideally CCMs should meet no more than on a quarterly basis with a maximum of 6 meetings per year. (ii) Each grant should have at least one field visit per year, but no more than two. Exceptions could be granted if related to low performing grants. (iii) not more than 10 persons attending the field visit. (iv) Non members invited by the CCM should not exceed 20% of the total membership. (v) Do not include CCM Secretariat staff or consultancy fees, as these costs are to be included in the Human Resources and Technical Assistance categories described above. (vi) Constituency meetings should follow a CCM meeting, ideally no more than on a quarterly basis with a maximum of 6 meetings per year. (vii) Constituency meetings should not include more than 20 persons. (viii) CCM Secretariat staff costs or consultancy fees are not included in this category as they are to be included in the Human Resources and Technical Assistance categories described above
| External Professional Services | Costs of all consultants (short or long term) providing technical or management assistance. This includes all costs related to the consultant such as consulting fees, travel and per-diems, field visits and other consultant costs relating to program planning. Technical Assistance may be used for technical or management assistance to support core CCM functions including civil society participation, program oversight and alignment with other national bodies. This includes all costs related to the consultant such as fees, travel and per-diem, field visits and other costs related to program planning and supervision. | (i) CCM funding cannot be used for hiring consultants to write proposals for Global Fund financing. (ii) Terms of reference for consultants hired by the CCM must include a specific clause prohibiting the writing of proposals by the consultant hired.
| Non-health Equipment | This category covers office furniture and equipment (laptop, beamer, digital camera, photocopier, etc). | (i) Vehicle purchase or vehicle long term lease are not eligible costs.
| Communication Material and Publications | Communication materials including printed materials and communication costs associated with core CCM functions (e.g., call for proposals, periodic reports of implementation status, minutes of meetings, website cost, newsletter, translation of key information, printing).
| Indirect and Overhead Costs | Overhead costs such as office rent, utilities, internal communication costs (mail, telephone, internet), insurance, fuel, security, cleaning. Management or overhead fees. | (i) Overhead costs are to be itemized and should not exceed 20% of the overall budget.
| Performance Areas | Definition
| Oversight | Oversight activities as Oversight commitees' meeting, visits and document sharing with CCM members
| Constituency engagement | Communication activities completed by he CCM to engage constituencies government and non -government.
| Operations | Activities to ensure Global Fund grants that are consistent with impact/outcome indicators in national strategy documents, relevant national bodies and other donors support. Activities to ensure CCM members are trained on them role and training to strenghten CCM representatives role.
| Sustainability and Transition | Activities to engage the CCM is prepared for and is taking into account sustainability and transition problematic in the response to the fight against the diseases as country.

## WorkPlan_Year_N (hidden)
CCM FUNDING AGREEMENT - COSTED WORK PLAN
Section 1. General Information
CCM Name: |  |  |  |  | Year of Agreement: | [6 empty] | GRAND TOTAL (Fixed Costs + Activities) = |  |  |  |  | 0
CCM Agreement No: |  |  |  |  | Year Starting Date:
Agreement Starting Date: |  |  |  |  | Annual Envelope
Section 2. Fixed costs and HR positions covered by CCM Funding Agreement
2A. Fixed Costs | [12 empty] | 2B. HR positions covered by this agreement. Please report all CCM Secretariat staff even if only a maximum 2 Full time equivalent positions can be covered by CCM Funding Agreement.
No. | Cost Grouping | Performance Area | Description | Total Year (in USD/EUR) |  | Assumptions / comments | [6 empty] | No. | Description |  |  | No. of positions financed by other sources | No. of positions financed by GF | Total No. of positions | Assumptions / Comments
1 | [12 empty] | 1 | [5 empty] | 0
2 | [12 empty] | 2 | [5 empty] | 0
3 | [12 empty] | 3 | [5 empty] | 0
4 | [12 empty] | 4 | [5 empty] | 0
5 | [12 empty] | 5 | [5 empty] | 0
|  |  | Total | 0 | [12 empty] | Total | 0 | 0
Section 3. Work Plan Activities
3A. CCM Activities |  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Budget | Assumptions / Comments
No. | Cost Grouping | Performance Area | Activities | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
1
2
3
4
5
6
7
8
9
10
0
3B. Investment on Civil society engagement (15% of the budget) |  |  | Minimum expected | Q1 M1: Approved; Q1 M3: Variance; Q2 M5: Comments
0 | bar: Q1 M3 to Q3 M7
Section 4. Co-funding. Mandatory for agreements above USD 300,000
No. | Cost Grouping | Performance Area | Description of funding support | Q1 M2: Budget (in USD/EUR); Q2 M4: Source of financing; Q3 M8: Comment
1 | bar: Q3 M8 to Q4 M12
2 | bar: Q3 M8 to Q4 M12
3 | bar: Q3 M8 to Q4 M12
4 | bar: Q3 M8 to Q4 M12
5 | bar: Q3 M8 to Q4 M12
0
Version November 2019
Note on G35: Variance against the total budget.

## ExpenditureCashBce_Year3
CCM FUNDING AGREEMENT EXPENDITURE AND CASH BALANCE REPORT
Section 1. General Information
CCM Name: |  | CCM El Salvador |  |  | Year of Agreement: |  | Year 3
CCM Agreement No: |  | SLV-CFUND-1707 |  |  | Year Starting Date: |  | 01 january 2019
Agreement Starting Date: |  | 01 January 2017 |  |  | Year Envelope |  | 31 october 2019
|  | BUDGET |  | EXPENDITURE | CURRENCY | ABSORPTION
GRAND TOTAL (Fixed Costs + Activities) = |  | 127139 |  | 128379.52 | USD | 101%
Section 2. Fixed costs and HR positions covered by CCM Funding Agreement
2A. Fixed Costs
No. | Cost Grouping | Performance Area | Description | Budget Approved | Expenditure | Expenditure rate | Reasons for Variance | pendiente | remanente | gasto | total
1 | Human Resources | Operations | Human Resources (Secretariat staffs) | 56014 | 46678.5 | 83.33% | El remanente de esta línea por $9,335,50 corresponde a salarios pendientes de noviembre y diciembre 2019, ya que este informe es al cierre del 31 de octubre. Se estima que el saldo de esta linea al 31 de diciembre sera de $0.00 | 9335.5 | 0 | 46678.5 | 56014
2 | Indirect and Overhead Costs | Operations | Office rental and supplies | 1000 | 164.2 | 16.42% | De esta linea se ha programado una compra de $401,73 la cual aparece como compromisos en el mes de noviembre. El saldo estimado al 31 de diciembre sera de $434,07 | 401.73 | 434.07 | 164.2 | 1000
3 | Indirect and Overhead Costs | Operations | Office rental and supplies | 26793 | 11657.25 | 43.51% | En esta linea hay compromisos pendientes por una suma de $11,328,91 (detallados en cuadro hoja de compromisos). se estima un remanente al 31 de diciembre por $3,806,84 | 11328.91 | 3806.84 | 11657.25 | 26793
4 | Indirect and Overhead Costs | Operations | Office rental and supplies | 672 | 410.27 | 61.05% | Esta linea tiene compromisos pendientes por $128.76, la diferencia con el saldo presupuestado obedece a que se programó un gasto mensual de $56.00; por lo que al 31 de diciembre, se reflejará un saldo de $132.97 | 128.76 | 132.97 | 410.27 | 672
5 | Indirect and Overhead Costs | Operations | Overhead cost - itemized fees to manage CCM funding (including audit) | 4500 | 3750 | 83.33% | El remanente en esta línea por $750.00 se debe a los pagos pendientes del mes de noviembre y diciembre 2019. El Saldo de esa linea al 31 de diciembre será $0.00 | 750 | 0 | 3750 | 4500
|  |  | Total | 88979 | 62660.22 | 70.42% |  | 21944.9 | 4373.88 | 62660.22 | 88979
2B. HR positions covered by this agreement. Maximum 2 Full time equivalent positions.
No. | Description | Approved | Reported | Reasons for Variance
1 | Executive Secretary | 1 | 1
2 | Administrative Assistant | 1 | 1
| Total | 2 | 2
Section 3. CCM Activities
3A. Costed Work Plan
No. | Cost Grouping | Performance Area | Activities | Budget approved | Expenditure | Expenditure rate | Reasons for Variance | pendiente | remanente
1 | Travel-related Costs | Oversight | CCM Plenary / General Assembly meeting | 3425 | 3831.85 | 111.9% | Se reportan $406,85 por sobre el monto autorizado, el cual se ha cubierto con los remanenes del 2018. Aun falta una actividad por un costo estimado de $605.00 que será utilizado para Plenaria 07-2019. Al 31 de diciembre esta linea reportará un sobregiro aproximado de ( $1,011,85) | 605 | -1011.85 | 3831.85 | 3425
2 | Travel-related Costs | Oversight | Oversight Committee meetings | 3425 | 3416.28 | 99.75% | las actividades se cumpliran segun lo programado. hay compromisos por $780.23 que seran utilizados para reunión de monitoreo con el Programa de TB MINSAL. Al 31 de diciembre esta linea reportará un sobregiro de ($771.51) | 780.23 | -771.51 | 3416.28 | 3425
3 | Travel-related Costs | Oversight | Technical Working groups meetings | 2512 | 2936.16 | 116.9% | En esta línea se han utilizado ($424.16 )sobre el monto presupuestado, debido a que se realizaron mas actividades de las programadas, para dar cumplimiento a las actividades solicitadas. Al 31 de diciembre esta linea presentara un saldo negativo de ($424.16) | 0 | -424.16 | 2936.16 | 2512
4 | Travel-related Costs | Oversight | Technical Working groups meetings | 457 | 676.51 | 148% | En esta línea se han utilizado ( $220.00 )sobre el monto presupuestado, debido a que fue necesario realizar una reunion adicional. Al 31 de diciembre se reflejará un saldo negativo de $219,51 | 0 | -219.51 | 676.51 | 457
5 | Travel-related Costs | Oversight | Technical Working groups meetings | 457 | 474.56 | 103.8% | En esta línea se han utilizado ( $18.00) sobre el monto presupuestado debido a aumento en el precio de referencia y numero de participantes en las actividades, el numero de actividades se cumplio según lo programado. al 31 de diciembre reflejará un saldo $17,56 | 0 | -17.56 | 474.56 | 457
6 | Travel-related Costs | Constituency Engagement | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | 3600 | 4128.16 | 114.7% | En esta línea se han utilizado $528.16 sobre el monto presupuestado. adicionalmente se cargará el pago de movilización a miembros por asistencia a diversas actividades del mes de diciembre por un monto estimado de $395.00 (El detalle esta en la hoja de compromisos). Se estima en esta linea un sobregiro al 31 de diciembre por( $923,16) | 395 | -923.16 | 4128.16 | 3600
7 | Travel-related Costs | Oversight | Site Visits / Monitoring Visits | 2800 | 2524.73 | 90.17% | Se dio cumplimiento a las actividades segun el plan de trabajo. Se cargaran a esta línea $1,118.64 que incluyen pago de movilización del mes de noviembre, gastos para actividades de visitas de campo,etc. (detalle en cuadro de compromisos) se estima al 31 de diciembre un sobregiro de ($843.37) | 1118.64 | -843.37 | 2524.73 | 2800
8 | Travel-related Costs | Constituency Engagement | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | 2284 | 1950.56 | 85.4% | las actividades se realizaron según lo programado. Pendiente de cargar en esta línea la compra de insumos para VII Foro de VIH que se esta organizando en el marco del dia mundial del VIH, por $246.01. el saldo de la linea al 31 de diciembre se estima en $87,43 | 246.01 | 87.43 | 1950.56 | 2284
9 | Travel-related Costs | Oversight | Workhops, Meetings and Training | 3500 | 3939.04 | 112.5% | En esta línea se han utilizado $439.04 sobre el monto presupuestado. Los cuales se cubriran con el remanente general del presupuesto. Al 31 de diciembre esta linea presentará un sobregiro de ( $439.04) Las actividades se cumplieron según lo programado. | 0 | -439.04 | 3939.04 | 3500
10 | Travel-related Costs | Oversight | Annual CCM retreat | 3500 | 0 | 0% | esta actividad se realizará el 20 y 21 de noviembre, se estima un gasto de $3751.88, se calcula que esta linea presentará un saldo al 31 de diciembre de ($251.88) | 3751.88 | -251.88 | 0 | 3500
11 | Communication Material and Publications | Oversight | Technical Support | 3200 | 2016.46 | 63.01% | Las actividades programas para esta linea se cumplieron segun el plan de trabajo. se tienen gastos pendientes de ocubre, noviembre y diciembre por $1,000.00. Al 31 de diciembre esta linea presentará un remante por $183.54 | 1000 | 183.54 | 2016.46 | 3200
12 | Travel-related Costs | Constituency Engagement | CCM Elections | 3500 | 4000 | 114.3% | En esta línea se han utilizado $500.00 sobre el monto presupuestado, los que seran cubiertos con remanentes del 2018. La línea al 31 de diciembre presentará un sobregiro de ($500.00) se realizaron mas actividades que las que se habian programado. | 0 | -500 | 4000 | 3500
13 | Travel-related Costs | Oversight | CCM Induction / Orientation | 3500 | 3983.99 | 113.8% | En esta línea se han utilizado $484.00 sobre el monto presupuestado, los que seran cubiertos con remanentes del 2018. al 31 de diciembre esta linea presentará un sobregiro de $483.99 | 0 | -483.99 | 3983.99 | 3500
14 | Travel-related Costs | Oversight | Technical Support | 2000 | 2000 | 100% | en correo del 27 de febrero, se recibio autorizacion para incorporar esta linea. La cual se utilizo al 100% | 0 | 0 | 2000 | 2000
|  |  | Total | 38160 | 35878.3 | 94.02% |  | 7896.76 | -5615.06 | 35878.3 | 38160
3B. Investment on Civil society engagement (15% of the budget) |  |  | Minimum expected | Approved | Reported | Variance | Reasons for Variance
|  |  | 18771 | 18771 | 35878.3 | 191.1% | Se realizaron actividades adicionales a las programadas, pues se contaba con remanente del año 2018
Section 4. Co-funding. Please include all additional support for CCM including staff.
No. | Cost Grouping | Performance Area | Description of funding support and source of financing |  | Expenses | Comment |  | 29841.66
1 | Travel-related Costs | Operations | Apoyo con movilización / MINSAL |  | 2550 | Movilización de miembros del MCP para asambleas y talleres y movilización de misiones oficiales
2 | Travel-related Costs | Operations | Apoyo local y alimentación/ URC |  | 400 | Local y alimentación en reuniones de Estrategia de Comunicaciones de CONAVIH
3 | Travel-related Costs | Operations | Apoyo movilización/ SISCA |  | 300 | Movilización de miembros en visitas de campo
4 | Travel-related Costs | Operations | Apoyo movilización/ PLAN |  | 20 | Movilización de miembros en visitas de campo
5 | External Professional Services | Sustainability, Transition and Linkages | Apoyo técnico/ USAID/PLAN |  | 2000 | Asistencia técnica con Estrategia de Sostenibilidad
6 | Travel-related Costs | Operations | Apoyo local y alimentación/ ONUSIDA |  | 525 | Local y alimentación en reuniones de comité de Etica
|  |  |  | Total | 5795
Section 6. Cash Reconciliation
Cash Outflow |  |  |  |  | Reported |  | Comments
Income |  | 1.1 | Cash Balance at the beginning of the period |  | 18834 |  | Remanente del año 2018 autorizado por el FM en actividades
|  | 1.2 | Disbursement from the Global Fund |  | 120000 |  | Desembolso FM año 3
Cash Outflow |  | 2.1 | Activities |  | -35878.3 |  | Gasto en actividades 2019
|  | 2.2 | Fixed costs |  | -62660.22 |  | Gasto en costos directos 2019
Commitments |  | 3.1 | Unpaid invoices, legal obligations, other obligations. |  | 29841 |  | Compromisos pendiente octubre, noviembre y diciembre 2019
|  |  | Total |  | 10454.48
Bank information |  | Reported | Comments
Cash Balance as per bank statements |  | 39296.68 | Ultimo estado de cuenta emitido por el banco al 31 de octubre 2019
Cash in transit for the reporting period |  | -966.76 | Cheques emitidos no cobrados al 31 de octubre 2019.
Cash in transit for the reporting period |  | 1965.42 | Devoluciones de efectivo no registradas al 31 de octubre 2019, $500.pertenecen a emision de cheque para caja chica no utilizados aun, pero registrados en banco.
Cash in transit after the current reporting period |  | -29841 | Compromisos pendientes por actividades de noviembre y diciembre 2019
Total |  | 10454.34
Version November 2019
Note on D66: Cash balance including commitments. Please specify the amount of commitments in the "Comments" section

## Compromisos
COMPROMISOS 2019
OCTUBRE
Linea | Descripción | Proveedor | Monto
SECCION COSTOS DIRECTOS
2 | envio de correspondencia | Mensajeria empresarial | 5
3 | Renta de oficina y administración | CLARO EL SALVADOR | 33.97
4 | líneas móviles | CLARO EL SALVADOR | 42.92
Subtotal |  |  | 81.89
SECCION ACTIVIDADES
1.1 | Caja chica | Karla Rivera
1.2 | conferencia de prensa mesa de VIH | Barcelo | 175.23
1.7 | Limpieza de chalecos visita de campo | Martinizing | 21.69
1.8 | Comité Organizador de Foro VIH | varios | 116.01
1.1 | coordinacion retiro anual | varios | 13.75
1.1 | Boletin que corresponde al Q3 | Rebeca Ayala | 200
| Mantto Web del mes | Christian Barrientos | 200
Subtotal |  |  | 726.68
TOTAL OCTUBRE |  |  | 808.57
NOVIEMBRE
SECCION COSTOS DIRECTOS
1 | Recursos Humanos | STAFF | 4667.75
2 | Insumos de oficina | Office Depot | 296.73
|  | Siman | 100
3 | Renta de oficina y administración | SISCA | 1056
|  | CLARO | 33.97
| Compra de laptop y licencia para actividades de campo (justificacipon comité de propuestas ) y bateria para laptop Dell | EQUISELE | 1500
| Compra de cañon para acitivades de campo (justificacipon comité de propuestas ) | ASSIT | 800
| Lente para cámara cannon para mejorar la calidad de fotografias de las actividades | RAF | 300
| Pago de alojamiento para la página web (servidor Blue Host)3 años | Christian Barrientos | 415
| Pago de dominio de pagina web (SV NET) 5 años | Christian Barrientos | 100
4 | Líneas móviles | CLARO | 42.92
5 | Overhead | SISCA | 375
Subtotal |  |  | 9687.37
SECCION ACTIVIDADES
1.7 | Movilización por actividades del mes | planilla de miembros | 235
| Pago por confección de chalecos monitoreo | multipromociones | 534.75
| Reunión de monitoreo con Unidad Ejecutora FM MINSAL Proyecto VIH | cajamarca | 327.2
1.1 | Retiro anual de miembros | Varios | 3738.13
1.11 | Mantto Web del mes | Christian Barrientos | 200
Subtotal |  |  | 5035.08
TOTAL NOVIEMBRE |  |  | 14722.45
DICIEMBRE
SECCION COSTOS DIRECTOS
1 | Pago de salario del mes Dirección Ejecutiva | STAFF | 4667.75
3 | Pago por alquiler del mes | SISCA | 1056
| Pago por línea movil 7602 6370 | CLARO | 33.97
| AUDITORIA | pte | 6000
4 | Pago por línea movil 78476001 | CLARO | 42.92
5 | Pago por overhead del mes | SISCA | 375
Subtotal |  |  | 12175.64
1.1 | Local y alimentación plenaria 07 | cajamarca | 605
1.2 | Reunión de monitoreo con Programa de TB MINSAL | cajamarca | 605
1.6 | Movilización por actividades del mes | planilla de miembros | 235
| Pago de transporte por plenaria 07 | pablitos tours | 160
1.8 | Insumos para VII Foro de VIH | variedades del centro | 30
| Diseño e impresión de diplomas para foro | Christian Barrientos | 100
1.11 | Mantto Web del mes | Christian Barrientos | 200
| Boletin Q4 | Rebeca Ayala | 200
Subtotal |  |  | 2135
TOTAL diciembre |  |  | 14310.64
Total pendiente de pago al cierre del año |  |  | 29841.66

## Libro de bancos
SISTEMA DE INTEGRACIÓN CENTROAMERICANA (SICA)
SECRETARIA DE LA INTEGRACIÓN SOCIAL CENTROAMERICANA (SISCA)
DIRECCIÓN DE ADMINISTRACIÓN Y FINANZAS
Conciliación Bancaria del 01 al 31 de octubre de 2019
Nombre del Proyecto: SISCA/MCP |  |  |  | Nombre de la Cuenta: La Secretaria de la Integración Social Centroamericana/MCP-ES
Nombre del Banco: Banco Davivienda, S.A. |  |  |  | Tipo de Cuenta: | Corriente
Sucursal: Santa Elena |  |  |  | Numero de la Cuenta: | 2510109367
Saldo según Estado de Cuenta Bancario: |  |  | 39296.68 | Saldo Según Registros: | 38329.92
(-)Cheques Pendientes de Pago |  |  | 966.76
Ch.N°362166 | Karla Eugenia Rivera Arévalo | 2019-10-31 | 600
Ch.N°362167 | Karla Eugenia Rivera Arévalo | 2019-10-31 | 37.93
Ch.N°362168 | Karla Eugenia Rivera Arévalo | 2019-10-31 | 54.36
Ch.N°362169 | Karla Eugenia Rivera Arévalo | 2019-10-31 | 130.33
Ch.N°362170 | Karla Eugenia Rivera Arévalo | 2019-10-31 | 17.42
Ch.N°362171 | Karla Eugenia Rivera Arévalo | 2019-10-31 | 39.52
Ch.N°362172 | Karla Eugenia Rivera Arévalo | 2019-10-31 | 87.2
Saldos Conciliados |  |  | 38329.92 |  | 38329.92 | 0

## anticipos
DETALLE DE ANTICIPOS
CHEQUE | MONTO | FECHA CHK | GASTO | FECHA GASTO | DEVOLUCIÓN | FECHA DEV
362153 | 3500 | 2019-09-18 | 2584.06 | 2019-09-25 | 915.94 | 2019-11-06 | Fortalecimiento a miembros
362160 | 550 | 2019-10-17 | 304 | 2019-10-30 | 246 |  | movilizacion de miembros oct
362161 | 350 | 2019-10-17 | 237.27 | 2019-11-22 | 112.73 | 2019-11-14 | Monitoreo
362166 | 600 | 2019-11-01 | 409.25 | 2019-10-24 | 190.75 | 2019-11-14 | plenaria 06-2019
| 5000 |  | 3534.58 |  | 1465.42

## List (hidden)
Cost Grouping | CCM Secretariat positions | Activities | Fixed Costs Activities
Human Resources | Executive Secretary | Annual CCM retreat | Human Resources (Secretariat staffs)
Indirect and Overhead Costs | Administrative Assistant | CCM Board meeting | Office rental and supplies
Non-health Equipment | Oversight Officer | CCM Elections | Office Equipement
External Professional Services | Finance Officer | CCM Induction / Orientation | Vehicule maintenance
Communication Material and Publications |  | CCM Plenary / General Assembly meeting | Overhead cost - itemized fees to manage CCM funding (including audit)
Travel-related Costs |  | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | Others (Please specify in comments)
Constituency engagement meetings (specify in comments)
|  | Others (Please specify in comments) | Performance Area
|  | Oversight Committee meetings | Operations
Year | Currency | Site Visits / Monitoring Visits | Oversight
Year 1 | USD | Technical Support | Constituency Engagement
Year 2 | EUR | Technical Working groups meetings | Sustainability, Transition and Linkages
Year 3 |  | Workhops, Meetings and Training
Year 4 (Exceptionnal) |  | Workshops, Meetings for Funding Request development
Workshops, Meetings for Grant Making
Assessment outcome | Yes/No | Workshops, Meetings for Reprogramming
Exceptional | Yes
Performing well | No
A few minor issues
Serious Issues

## CCMRCM (hidden)
CCM Afghanistan
CCM Albania
CCM Algeria
CCM Angola
CCM Armenia
CCM Azerbaijan
CCM Bangladesh
CCM Belarus
CCM Belize
CCM Benin
CCM Bhutan
CCM Bolivia
CCM Bosnia and Herzegovina
CCM Botswana
CCM Bulgaria
CCM Burkina Faso
CCM Burundi
CCM Cambodia
CCM Cameroon
CCM Central African Republic
CCM Chad
CCM Colombia
CCM Comoros
CCM Congo (Democratic Republic)
CCM Congo (Republic of)
CCM Costa Rica
CCM Cote d'Ivoire
CCM Cuba
CCM Djibouti
CCM Dominican Republic
CCM Ecuador
CCM El Salvador
CCM Eritrea
CCM Ethiopia
CCM Fiji
CCM Gabon
CCM Gambia
CCM Georgia
CCM Ghana
CCM Guatemala
CCM Guinea
CCM Guinea-Bissau
CCM Guyana
CCM Haiti
CCM Honduras
CCM India
CCM Indonesia
CCM Iran (Islamic Republic of)
CCM Jamaica
CCM Kazakhstan
CCM Kenya
CCM Kosovo
CCM Kyrgyzstan
CCM Lao PDR
CCM Lesotho
CCM Liberia
CCM Macedonia
CCM Madagascar
CCM Malawi
CCM Malaysia
CCM Mali
CCM Mauritania
CCM Mauritius
CCM Moldova
CCM Mongolia
CCM Montenegro
CCM Morocco
CCM Mozambique
CCM Myanmar
CCM Namibia
CCM Nepal
CCM Nicaragua
CCM Niger
CCM Nigeria
CCM Pakistan
CCM Panama
CCM Papua New Guinea
CCM Paraguay
CCM Peru
CCM Philippines
CCM Romania
CCM Russian Federation
CCM Rwanda
CCM São Tomé and Príncipe
CCM Senegal
CCM Sierra Leone
CCM Solomon Islands
CCM South Africa
CCM South Sudan
CCM Sri Lanka
CCM Sudan
CCM Suriname
CCM Swaziland
CCM Tajikistan
CCM Tanzania
CCM Thailand
CCM Timor Leste
CCM Togo
CCM Tunisia
CCM Uganda
CCM Ukraine
CCM Uzbekistan
CCM Viet Nam
CCM Zambia
CCM Zanzibar
CCM Zimbabwe
Non-CCM Somalia
RCM Abidjan-Lagos Corridor Organisation
RCM African Regional Coordinating Mechanism
RCM Asia (Regional Steering Committee)
RCM EMMIE (Mesoamerica)
RCM Organisation of Eastern Caribbean States
RCM Pan Caribbean Partnership against HIV/AIDS
RCM Regional Coordinating Mechanism for the Regional Response to TB in the mining sector in Southern Africa
RCM Western Pacific
RO Comite Asesor Regional para subvenciones del Fondo Mundial en America Latina y el Caribe – CAR LAC