## Instructions_WorkPlan_En
Costed Work Plan for CCM Funding Agreements
- As part of the CCM Funding Agreement, the Costed Work Plan is a legal document that supports the disbursements to cover the CCM Activities and CCM Secretariat costs financed by the Global Fund, as per the CCM Guidelines.
- The CCM Secretariat should always keep the track and documentation on the estimation of costs presented in this Costed Work Plan.
- The information reflected in this document will serve to track the execution of activities and the detailed budget that will be kept by the CCM for accountability purpose, LFA verification and Audits.
- The Costed Work Plan contains 4 sections 1. General Information 2. Fixed costs and HR positions covered by the CCM Funding Agreement 3. CCM Activities 4. Co-funding
- In general, only the yellow cells can be filled in free format. Some drop-downs (cells in grey) and formulas are part of the document, we request to please not modify them, in order to obtain a standardized document across all the CCMs financed by the Global Fund.
-The Section 1 "General information" reflects the basic information about the CCM Funding Agreement
- At the top of the document the table "Grand Total" shows the final amount to be covered by the CCM Funding Agreement. It coincides with the corresponding year amount highlighted in the Facesheet.
The Section 2 "Fixed costs and HR positions covered by CCM Funding Agreement" includes any CCM Secretariat recurrent cost. This category containes 2 separated tables to summarize the fixed costs, making sure the categories are grouped so that there is one "Cost Grouping" per line, and the costs related to the Human Resources.
- The Section 3 "CCM Activities" shows the planning of activities throughout the year, and the corresponding budget. The list of activities is standard for all the CCMs, any detailed or specific name that could refer to the CCM budget can be added in the assumptions or comments column.
- Inside the table of the Section 3, the column "Total No of Activities" must quantify the number of activities planned for the year as per the information filled in the columns "M1…M12". The column "Budget" shows the total cost for the line in the agreed currency (US$/EUR) for the CCM Funding.
- The Columns "Costs Grouping" and "Performance Area" respond to the approved terms by the Global Fund.
- The table of the section 4 "Co-funding" is mandatory only if the 3-year budget is above USD 300,000. However, all the CCMs invited to include the total financial needs for an ideal functionning of the CCM.
- Please refer to the Spreadsheet "Definitions" for a detailed description of all the Cost Groupings and the Performance Areas used in this Costed WorPlank.
- Please refer to the Spreadsheet "Lists" for a complete overview of all the category options you can use to fill this Costed Work Plan.
Version June 2020

## Instructions_WorkPlan_Fr
Plan de travail chiffré pour les Accords de financement des CCM
-Dans le cadre de l'Accord de financement du CCM, le plan de travail chiffré est un document juridique qui soutient les décaissements pour couvrir les coûts des activités du CCM et du Secrétariat du CCM financés par le Fonds mondial, conformément aux Lignes directrices du CCM.
- Le Secrétariat du CCM doit toujours conserver la trace et la documentation sur l'estimation des coûts présentée dans ce plan de travail chiffré.
- L'information contenue dans ce document servira à suivre l'exécution des activités et le budget détaillé qui seront conservés par le CCM à des fins de responsabilité, de vérification de l'ALF et d'audit.
- Le plan de travail chiffré est composé de 4 sections: 1. Information générale 2. Coûts fixes et les postes de RH couverts par l'accord de financement du CCM 3. Activités du CCM 4. Co-financement
- En général, seules les cellules jaunes peuvent être remplies en format libre. Certaines listes déroulantes (cellules en gris) et les formules font partie du document, nous vous demandons de ne pas les modifier, et ce afin d'obtenir un document standardisé pour tous les CCM financés par le Fonds mondial.
-La section 1 "General Information" ("Information générale") reflète les informations de base de l'Accord de financement du CCM
- En haut du document, le tableau "Grand Total" indique le montant final couvert par l'Accord de financement du CCM. Il coïncide avec le montant de l'année correspondante surligné dans la Facesheet.
- La section 2 "Fixed costs and HR positions covered by CCM Funding Agreement" ("Frais fixes et postes de RH couverts par l'Accord de financement du CCM") comprend tout coût récurrent du Secrétariat du CCM. Cette catégorie contient 2 tableaux séparées pour résumer les coûts fixes, en s'assurant que les catégories sont regroupées de sorte qu'il y ait un "groupement des coûts" ("Cost Grouping") par ligne et les coûts liés aux ressources humaines.
- La section 3 "CCM Activities" ("Activités du CCM") montre la planification des activités tout au long de l'année et le budget correspondant. La liste des activités est standard pour tous les CCM, tout nom détaillé ou spécifique qui pourrait se référer au budget du CCM peut être ajouté dans la colonne des hypothèses ou des commentaires.
- Dans le tableau de la section 3, la colonne "Total of activities" ("Nombre total d'activités") doit quantifier le nombre d'activités prévues pour l'année selon les informations remplies dans les colonnes "M1 ... M12". La colonne " Budget" indique le coût total de la ligne dans la devise convenue (US $ / EUR) pour le financement du CCM.
- Les Colonnes "Cost Grouping" ("Groupement de coûts") et "Performance Area" ("Zone de performance") répondent aux termes approuvés par le Fonds mondial.
- Le tableau de la section 4 "Co-financing" ("Co-financement") est obligatoire uniquement si le budget pour 3 ans est supérieur à USD 300,000. Cependant, tous les CCM ont été invités à inclure les besoins financiers totaux pour un fonctionnement idéal.
- La section 5 "Special Conditions" ("Conditions spéciales") résume l'état des conditions spéciales énoncées dans l'Accord de financement du CCM.
- Veuillez vous référer à la feuille de calcul "Definitions" (disponible uniquement en anglais) pour une description détaillée de tous les groupements de coûts et des zones de performance utilisées dans ce plan de travail chiffré.
- Veuillez consulter la feuille de calcul "Lists" (liste disponible uniquement en anglais) pour un aperçu complet de toutes les options de catégorie que vous pouvez utiliser pour remplir ce plan de travail chiffré.
Version juin 2020

## Instrucciones_WorkPlan_Es
Plan de trabajo costeado para los Acuerdos de financiamiento de los MCP
- Como parte del Acuerdo de Financiación del MCP, el Plan de trabajo costeado es un documento legal que apoya los desembolsos para cubrir los costos de las actividades del MCP y de la Secretaría del MCP financiados por el Fondo Mundial, de acuerdo con las Directrices del MCP.
- La Secretaría del MCP debe guardar siempre un registro y la documentación sobre la estimación de costos presentada en este Plan de trabajo costeado.
- La información reflejada en este documento servirá para rastrear la ejecución de las actividades y el presupuesto detallado que mantendrá el MCP para fines de rendición de cuentas, verificación del ALF y Auditorías.
- El Plan de trabajo costeado tiene 4 secciones: 1. Información general 2. Costos fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP 3. Actividades del MCP 4. Contrapartida
- En general, sólo las celdas amarillas se pueden rellenar en formato libre. Algunos desplegables (celdas en gris) y fórmulas forman parte del documento, solicitamos no modificarlos, a fin de obtener un documento estandarizado para todos los MCPs financiados por el Fondo Mundial.
-La Sección 1 "General Information" ("Información general") refleja la información básica sobre el Acuerdo de financiamiento del MCP
- En la parte superior del documento, el cuadro "Grand Total" muestra el monto final que será cubierto por el Acuerdo de financiamiento del MCP. Coincide con la cantidad del año correspondiente resaltada en la Facesheet.
- La Sección 2 "Fixed costs and HR positions covered by CCM Funding Agreement" ("Costos fijos y posiciones de recursos humanos cubiertos por el Acuerdo de financiamiento del MCP") incluye cualquier costo recurrente de la Secretaría del MCP. Esta categoría contiene 2 tablas separadas para resumir los costos fijos, asegurándose de que las categorías se agrupan de manera que haya una "Agrupación de Costos" ("Cost Grouping") por línea y los costos relacionados con recursos humanos.
- La Sección 3 "CCM Activities" ("Actividades del MCP") muestra la planificación de las actividades a lo largo del año y el presupuesto correspondiente. La lista de actividades es estándar para todos los MCP, cualquier nombre detallado o específico que pudiera referirse al presupuesto del MCP se puede agregar en la columna de supuestos o comentarios.
- Dentro de la tabla de la Sección 3, la columna "Total No of Activities" ("Número Total de Actividades") debe cuantificar el número de actividades previstas para el año según la información presentada en las columnas "M1 ... M12". La columna "Budget" ("Presupuesto") muestra el costo total de la línea en la moneda acordada (USD/EUR) para el financiamiento del MCP.
- Las columnas "Costs Grouping" ("Agrupación de costos") y "Performance Area" ("Área de desempeño") responden a los términos aprobados por el Fondo Mundial.
- El cuadro de la sección 4 "Co-funding" ("Contraparte") es obligatorio únicamente si el presupuesto a 3 años supera los USD 300.000. Sin embargo, todos los MCPs fueron invitados a incluir las necesidades financieras totales para un funcionamiento ideal del MCP.
- Consulte la pestaña "Definitions" (únicamente disponible en inglés) para obtener una descripción detallada de todas las agrupaciones de costos y las áreas de desempeño utilizadas en este Plan de trabajo costeado.
- Consulte la pestaña "Lists" (únicamente disponible en inglés) para obtener una descripción completa de todas las opciones de categoría que puede utilizar para llenar este Plan de trabajo costeado.
Versión Noviembre 2019

## Definitions
Instructions
A. General instructions
1 | Which worksheets to complete | The CCM funding application requires the CCM to complete the following worksheets: ► Performance framework ► Detailed budget - Period 1 including detailed assumptions ► Detailed budget - Period 2 including detailed assumptions ► Co-Payment ► CCM funding request form
The following forms will be automatically generated: - Work plan - Summary budget per performance area, per Cost Grouping and per source of fund (SOF)
Additionally the CCM may include other worksheets or attachments to provide additional information to support the detailed budget e.g. to support a costing assumption.
2 | Recommended steps in completing the template | ! CAUTION : PLEASE NOTE THAT THIS TEMPLATE CONTAINS MACROS. You should ensure that you have the right setting: On the Menu Bar, Select “Tools”, then move the cursor over “Macro” and select “Security”. From the options select “Medium” and then select “Ok”. Close the file and re-open it. You will receive a security warning. Select “Enable Macros”. This will enable all the features of the Budget Toolkit to be fully active.
3 | Cell formatting | Below the applicant is taken through an explanation of the intended data to be entered in each column of the template. Note that most cells have fixed formatting which should not be adjusted unless absolutely necessary.
6 | Information sources | If applicants have any technical difficulty in using this template or are unsure about any aspect of it, guidance may be obtained from the Global Fund through sending an e-mail to ccm@theglobalfund.org
B. Specific instructions for data entry, by each column header - Menu
| Column header | Instructions | Possible check?
| Menu | ►Region, Country, CCM are to be selected from the drop down lists. ►Enter in the name of the recipient organization. The GF Secretariat will enter the Agreement number.
C. Specific instructions for data entry, by each column header - Performance Framework
| Column header | Instructions | Possible check?
Section A. General information
| Funding start date | ►Enter Day, Month and Year (numeric values) for the intended start of the funding period. Final date will be determined by the Global Fund based on completion of the application review process.
| Year 1 and Year 2 | This section gives information on the reporting periods over the funding term, dates when progress updates and disbursement requests (PUDR) are due. Based on a 12 continuous month periods, the cells will be populated automatically. The reporting periods could be aligned with national reporting cycle. For any change in the proposed format, pls submit your request to the CCM Team. | Progress Update and Disbursement request are due one month upon completion of Q3 and Q7 (month 10 and month 22 respectively).
| Section B. Overall goal and objective | Goal and Objectives are broad and overarching statements of long term outcome of the program and should be consistent with the strategy defined by the CCM during the planning exercise. ►Each strategic objective should be in line with the Performance areas defined by the Global Fund.
| Section C. Performance Framework | Performance Area ►Select a key Performance Area as defined under Section B above. A drop-down list shows the areas applicable to CCM funding. This field cannot be overwritten.
| Section C. Performance Framework | Selection of Indicator(s): ► Indicator #1 ' % of planned oversight activities completed with documented participation by all CCM constituencies' is compulsory. All CCMs applying for expanded funding should provide base line data and set targets (intended results) for this indicator. ► Subsequent indicators are to be selected from the GF core list, in line with the overall objectives defined in Section B above. The CCM Team recommends that the maximum number of indicators for a two year plan is five. ► On exceptional cases, CCMs can propose to measure an indicator outside the GF core list of indicators. Those indicators will have to be reviewed and approved by the CCM Team before the funding request can be finalized by the CCM and submitted to the GF. ► Indicators should be numbered sequentially in the first column of this section. | Information has to be provided in all cells relating to each indicator. The indicator number cell will turn RED when information is missing.
| Section C. Performance Framework | Setting baselines ►baselines must be provided for each of the selected indicator with a clear data source, ideally a reference document. If baselines cannot be given at the onset of the program, they should be established. Setting targets ►targets should be cumulative and set according to when the indicators will be measured. Tied to other donors (Y/N) ►Whether the target reflects solely Global Fund financing through the current grant (Tied Yes - activities are funded solely by the current grant) or co-financed (Not tied when targets are not directly tied to GF financing, when GF resources contribute and thus are shared between all donors involved). Baselines include targets ►In this column you should select 'Yes' or 'No' from the drop down list to indicate whether or not baselines are included in each target. In general, the baseline is to be included. | For baselines, supporting documentation will have to be provided for future verification by the LFA.
D. Specific instructions for data entry, by each column header - Detailed budgets Period 1 and Period 2
As noted above, when a line of data is entered in the "Detailed budget - Year 1" the same Reference Number, objective, Performance Area, activity and Cost Grouping will automatically be repeated on the Year 2 detailed budget sheets ("Detailed budget - Year 2"). Note that it does not mean that each activity line has to be completed with cost data (i.e. with unit cost and quantity data) in each year. If there is no budget data for an activity in a year, you should enter zeros. If you have a NEW activity in "Detailed budget - Year 2" you must enter the activity in "Detailed budget - Year 1" (with zero cost in year 1), so that the activity is automatically copied into the following years.
!Caution: Applicants should not add any totals or sub-totals in any worksheet within the template as this will interfere with the logic of the budget summaries.
Applicants will note that the detailed budget worksheets ("Detailed budget - Year 1" and "Detailed budget Year 2" ) are automatically totaled and analyzed into the summary budget worksheet ("Summary budget, by Cost Grouping, Performance Area and source of fund (SOF)"). This involves the use of pivot tables that have been pre-set to analyze the data input. Applicants should not attempt to adjust these tables as this may corrupt their functioning.
| Column header | Instructions | Possible check?
| Objective Number | This number refers to the objective defined in section B - Overall goals and objectives in the performance framework worksheet and for which a budget activity is to be defined.
| Performance Area | The performance area will be populated automatically based on the information provided in Section B of the performance framework sheet.
| Activity | In the column you should describe clearly and concisely, the planned budget activity. The wording should be consistent with that used in the work plan.
| Directly related indicator | This column has been included to easily show the link between the budget and the Performance Framework. A reference should be entered where the activity matches with a target within the Performance Framework. The number entered should be the indicator number referenced in the Performance Framework. | Cross check from the Performance Framework to see that all directly related budget activities show a reference to the relevant indicator
| Assumptions | This column requires a short description of the detailed assumptions used to arrive at the budget amount and may make cross reference to a detailed document submitted with this request for funding. Budget assumptions should provide sufficient information to be able to determine how unit quantities and unit costs were calculated. | Confirm that the assumptions spelled out comply with the requirement that all key assumptions, including unit costs and quantities should be provided.
| Cost categories | This is a drop down list of 8 defined cost categories. Each budget activity should be associated with a Cost Grouping. For further description of the categories refer to the Definition table. | Check that the allocation follows the Global Fund Cost Grouping descriptions contained in the guidelines. Ensure costs are eligible for GF funding as per the definition and limitations stated in this section of the application form.
| Measurement unit | This is the unit of measurement to which the unit cost (in the next column) refers. It will depend on the nature of the activity and the complexity of the costing method. Examples may include: monthly salary cost per person, cost per meeting, cost of a site visit, etc. Note that costs such as Human Resources showing a simple multiplication of unit cost by quantity may not be appropriate in the template. Applicants should explain the detailed assumptions of Human Resources costs in the worksheet "detailed assumptions" or refer to a separate document. | Ensure clear and concise information is provided for LFA and GF review of the application.
| Unit cost | This is the unit cost of the item described in the preceding column in the currency defined in Section A. General information - Performance Framework worksheet. Budget assumptions should provide sufficient information to be able to determine how unit costs were calculated. If the item is costed in a currency other than the proposed currency, the working to convert the unit cost to the defined currency should be shown in the "Detailed assumptions" worksheet. If there is a differential unit cost for the same activity line in the same quarter then a separate row should be added in the budget, and the calculation explained in the "Detailed assumptions worksheet".
| Quantity | This will be the actual quantity for which the cash budget is required. Note: budget assumptions should provide sufficient information to be able to determine how unit quantities were calculated. | Where the activity has a directly related target in the Performance Framework, ensure the budget is consistent with the Performance Framework.
| Total amount | This cell contains a formula which multiplies the Unit cost by the Quantity by quarter in Years 1 and 2. | No specific checks proposed
| Total quantity Period 1 / Total quantity Period 2 | This is a formula which sums the four quarterly quantities to give the annual quantity. | Where the activity has a directly related target in the Performance Framework, ensure the budget is consistent with the Performance Framework. If there are differences, this should be explained in the "Detailed assumptions" worksheet.
| Total amount Period 1 / Total amount Period 2 | This is a formula which sums the four quarterly budget amounts in the proposal currency to give the annual budget. | Ensure the reported amounts are accurate.
E. Other Sources of funding (SOF)
| Column header | Instructions | Possible check?
CCMs applying for more than USD100,000 per year are required to report in this section the source of funds and amounts mobilized as required under the CCM funding policy.
| Summary funding distribution | Global Fund Amount The cells corresponding to 'GF Funding amount' will be populated automatically based on the information provided in sheets 'detailed budget Year 1' and 'detailed budget Year 2' . | Amounts specified under this section of the report are accurate and supported by clear documentation for future verification.
Source of funds (SOF)1, 2, etc ►For each non GF funding you will specify the funding source and the amount committed for the CCM. ►Under Section 2 of the form (Section 2 Detailed funding information) you will have to specify the percentage of this amount going to ‘Secretariat support Costs’ and the percentage going specifically to support directly CCM performance costs. ►For the amount to support CCM performance costs, you are then required to specify the percentage which is allocated for each performance area (oversight, constituency engagement, alignment, capacity building / gender).
F. CCM funding request form
| Column header | Instructions | Possible check?
Section A: budget summary
| A1 to A7 | Information in this section will be uploaded with data entered in different parts of the form. | Verify information in this section of the report is accurate and matches information entered in other parts of the form (detailed and summary budgets).
Section B: recipient entity information
| B1 | Name of the recipient entity is populated automatically. ►Sector has to be specified.
| B2 to B5 | ►Complete information has to be entered | Ensure all information is complete and accurate.
Section C: CCM approval
|  | ►Name and title information has to be provided for each CCM Member. The funding application is completed only when it has been signed by all members. Original document is to be submitted to the Global Fund Secretariat. | Ensure all information is complete and accurate.
| Others | Others significant costs which do not fall under the above-defined cost group. Costs under this cost group are to be clearly specified.
Definitions
NOTE: The CCM Secretariat should always keep the track and documentation on the estimation of costs and the variation agains the budget.
| Cost grouping | General Description | Limitations
| Human Resources | Salaries, wages and related costs (pensions, incentives, supplements, top ups, and other employee benefits, etc.) relating to all employees (including field personnel), and employee recruitment costs. Eligible costs under this cost grouping are the salaries of CCM Secretariat staff. | (i) Secretariat staff should not exceed 2 persons. (ii) Scope of work for key personnel is to be submitted to the GF CCM Team for approval. (iii) CCM funding shall not be used to remunerate CCM members. (iv) Salaries must be commensurate with national salary scales.
| Travel-related Costs (includes meetings' expenses) | Workshops, meetings, training publications, training-related travel, including training per-diems. Do not include human resources costs related to training which should be included under the Human Resources category. Constituency consultations for non government constituencies only (e.g. civil society) and processes to promote and improve the quality of stakeholder participation, including travel costs for civil society participation. Eligible costs under this group of activities includes (i) CCM general meeting expenses, travel costs for members to attend CCM meetings, CCM support costs. (ii) Expendable equipment, office supplies, travel, field visits and other costs relating to program planning and administration. Legal, accounting costs, bank charges, etc. | (i) Ideally CCMs should meet no more than on a quarterly basis with a maximum of 6 meetings per year. (ii) Each grant should have at least one field visit per year, but no more than two. Exceptions could be granted if related to low performing grants. (iii) not more than 10 persons attending the field visit. (iv) Non members invited by the CCM should not exceed 20% of the total membership. (v) Do not include CCM Secretariat staff or consultancy fees, as these costs are to be included in the Human Resources and Technical Assistance categories described above. (vi) Constituency meetings should follow a CCM meeting, ideally no more than on a quarterly basis with a maximum of 6 meetings per year. (vii) Constituency meetings should not include more than 20 persons. (viii) CCM Secretariat staff costs or consultancy fees are not included in this category as they are to be included in the Human Resources and Technical Assistance categories described above
| External Professional Services | Costs of all consultants (short or long term) providing technical or management assistance. This includes all costs related to the consultant such as consulting fees, travel and per-diems, field visits and other consultant costs relating to program planning. Technical Assistance may be used for technical or management assistance to support core CCM functions including civil society participation, program oversight and alignment with other national bodies. This includes all costs related to the consultant such as fees, travel and per-diem, field visits and other costs related to program planning and supervision. | (i) CCM funding cannot be used for hiring consultants to write proposals for Global Fund financing. (ii) Terms of reference for consultants hired by the CCM must include a specific clause prohibiting the writing of proposals by the consultant hired.
| Non-health Equipment | This category covers office furniture and equipment (laptop, beamer, digital camera, photocopier, etc). | (i) Vehicle purchase or vehicle long term lease are not eligible costs.
| Communication Material and Publications | Communication materials including printed materials and communication costs associated with core CCM functions (e.g., call for proposals, periodic reports of implementation status, minutes of meetings, website cost, newsletter, translation of key information, printing).
| Indirect and Overhead Costs | Overhead costs such as office rent, utilities, internal communication costs (mail, telephone, internet), insurance, fuel, security, cleaning. Management or overhead fees. | (i) Overhead costs are to be itemized and should not exceed 20% of the overall budget.
| Performance Areas | Definition
| Oversight | Oversight activities as Oversight commitees' meeting, visits and document sharing with CCM members
| Constituency engagement | Communication activities completed by he CCM to engage constituencies government and non -government.
| Operations | Activities to ensure Global Fund grants that are consistent with impact/outcome indicators in national strategy documents, relevant national bodies and other donors support. Activities to ensure CCM members are trained on them role and training to strenghten CCM representatives role.
| Sustainability and Transition | Activities to engage the CCM is prepared for and is taking into account sustainability and transition problematic in the response to the fight against the diseases as country.

## WorkPlan_Year_N
CCM FUNDING AGREEMENT - COSTED WORK PLAN
Section 1. General Information
CCM Name: |  | CCM El Salvador |  |  | Year of Agreement: |  |  | Year 2 |  |  |  | GRAND TOTAL (Fixed Costs + Activities) = |  |  |  |  | 128011
CCM Agreement No: |  | SLV-CFUND-2008 |  |  | Year Starting Date: |  |  | 2021-01-01
Agreement Starting Date: |  | 2020-01-01 |  |  | Annual Envelope |  |  | 2
Section 2. Fixed costs and HR positions covered by CCM Funding Agreement
2A. Fixed Costs | [12 empty] | 2B. HR positions covered by this agreement. Please report all CCM Secretariat staff even if only a maximum 2 Full time equivalent positions can be covered by CCM Funding Agreement.
No. | Cost Grouping | Performance Area | Description | Total Year (in USD/EUR) |  | Assumptions / comments | [6 empty] | No. | Description |  |  | No. of positions financed by other sources | No. of positions financed by GF | Total No. of positions | Assumptions / Comments
1 | Human Resources | Operations | Human Resources (Secretariat staffs) | 60681 |  | salarios y prestaciones; incluye aguinaldo para cada una de las posiciones. | [6 empty] | 1 | Executive Secretary |  |  |  | 1 | 1
2 | Indirect and Overhead Costs | Operations | Office rental and supplies | 1000 |  | compra de insumos de oficina | [6 empty] | 2 | Administrative Assistant |  |  |  | 1 | 1
3 | Indirect and Overhead Costs | Operations | Office rental and supplies | 22000 |  | costos de administracion (incremento de costos por tercer funcionario, especialista en monitoreo para 2021) | [6 empty] | 3 | [5 empty] | 0
4 | Indirect and Overhead Costs | Operations | Overhead cost - itemized fees to manage CCM funding (including audit) | 4500 |  | overhead | [6 empty] | 4 | [5 empty] | 0
5 | [12 empty] | 5 | [5 empty] | 0
|  |  | Total | 88181 | [12 empty] | Total | 2 | 2
Section 3. Work Plan Activities
3A. CCM Activities |  |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Budget | Assumptions / Comments
No. | Cost Grouping | Performance Area | Activities | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
1 | Travel-related Costs | Oversight | CCM Plenary / General Assembly meeting | [12 empty] | 2320 | Asambleas plenarias con la participación de todos los sectores (4 presenciales y 2 virtuales) para dar seguimiento a la ejecución de los proyectos, continuar con el proceso de presentacion de nuevas propuestas de país y el proceso de negociacion con el FM, dar seguimiento a propuestas multipais (VIH y TB), se facilita la coordinación con otros mecanismos nacionales y regionales, retroalimentación de los sectores del trabajo del MCP-ES. Inlcuye gastos para conectividad | bar: Q1 M2; Q2 M4; Q2 M6; Q3 M8; Q4 M10; Q4 M12
2 | Travel-related Costs | Oversight | Oversight Committee meetings | [12 empty] | 2320 | Reuniones del comité de monitoreo estratégico (4 presenciales y 2 virtuales) con todos los sectores representados en el MCP-ES y los RP´s, donde se comparten y analizan los tableros de mando, se da seguimiento a las recomendaciones del comité de monitoreo y a las decisiones del MCP-ES, se comparten los informes de las visitas de campo y otros temas como por ejemplo la distribucion de medicamentos y casos de TB. Inlcuye gastos para conectividad. | bar: Q1 M1; Q1 M3; Q2 M5; Q3 M7; Q3 M9; Q4 M11
3 | Travel-related Costs | Oversight | Technical Working groups meetings | [12 empty] | 2280 | El Comité Ejecutivo se reunirá con los RP y los coordinadores y subcoordinadores de los comités permanentes una semana previa a la reunión plenaria, para dar seguimiento a los proyectos en ejecucion, se identifican los problemas, se revisan las posibles reprogramaciones si fuese necesario, y otras actividades relacionadas con la operatividad del MCP-ES. Especialmente durante estas reuniones se dará seguimiento a la preparación de solicitudes de Fondos a ser presentadas en el mes de febrero y posteriormente al proceso de negociacion con el FM. a traves de estas reuniones se dara seguimiento al proceso deCCM Evolution. | bar: Q1 M2 to Q4 M11
4 | Travel-related Costs | Oversight | Technical Working groups meetings | [12 empty] | 1160 | Los comités de capacitación y comunicaciones sostendrán una reunión trimestral de manera conjunta (2 virtuales y 2 presenciales), donde se planificará el programa de fortalecimiento de los miembros del MCP-ES y la búsqueda de asistencia técnica para el desarrollo de los temas, además en las reuniones se dará seguimiento a la implementación de la estrategia de comunicaciones, que garantiza la transparencia del trabajo del MCP-ES en la implementacion de los proyectos de pais. Inlcuye gastos para conectividad. | bar: Q1 M1; Q2 M4; Q3 M7; Q4 M10
5 | Travel-related Costs | Constituency Engagement | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | [12 empty] | 3750 | Movilización de miembros de sociedad civil para promover la participación en las actividades del MCP-ES. Es un calculo historico, se hace en base al número de reuniones programadas y miembros de sociedad civil a los que se les provee apoyo. | bar: Q1 M1 to Q4 M12
6 | Travel-related Costs | Oversight | Site Visits / Monitoring Visits | [12 empty] | 3000 | Para dar seguimiento a los proyectos y validar la información presentada por los RP en los tableros de mando se realizarán 4 visitas de campo por semestre, (2 de VIH, 1 de Tb y 1 para proyectos Multipais). Se espera que la mayoría de los miembros del MCP-ES participen en al menos una de las visitas, se invitará también a otras personas que no son miembros del MCP-ES, se dá prioridad a la participación de personas de las poblaciones clave y afectadas. | bar: Q1 M2 to Q2 M4; Q2 M6 to Q3 M8; Q4 M10 to Q4 M11
7 | Travel-related Costs | Constituency Engagement | Constituency engagement meetings (specify in comments) | [12 empty] | 6000 | Reuniones presenciales y virtuales, para la implementación de planes de trabajo de los miembros de socidad civil. Inlcuye gastos para conectividad. | bar: Q1 M3; Q3 M7; Q4 M10
8 | Travel-related Costs | Oversight | Workhops, Meetings and Training | [12 empty] | 4000 | Taller de dos días para fortalecer a los miembros en Monitoreo Estrategico. Los fondos solicitados incluyen, facilitacion, costos de alimentación, local, materiales fungibles y transporte. | bar: Q3 M9
9 | Travel-related Costs | Oversight | Annual CCM retreat | [12 empty] | 5000 | Retiro anual de miembros, evaluación del trabajo del 2021 y elaboración del Plan Operativo del 2022 , el costo incluye, alojamiento, alimentación para dos días, transporte y articulos promocionales para la actividad a compartir con los miembros. | bar: Q4 M11
10 | Travel-related Costs | Oversight | Others (Please specify in comments) | [12 empty] | 4000 | Durante el año se elaborarán 4 boletines informativos de manera electrónica, para dar a conocer las actividades que desarrolla el mecanismo, se actualizarán mensualmente la página web y las redes sociales para compartir la información con el público en general y los sectores constituyentes se prevé tambien elaborar sistemazacion de dialogos desarrollados. | bar: Q1 M1 to Q4 M12
11 | Travel-related Costs | Oversight | Technical Working groups meetings | [12 empty] | 6000 | Reuniones del Comité de propuestas para la elaboración y negociacion de las Solicitudes de fondos de VIH y TB, con la participación de miembros de sociedad civil y equipos técnicos de cada programa y de los RPs. | bar: Q1 M1 to Q4 M12
39830
3B. Investment on Civil society engagement (15% of the budget) |  |  | Minimum expected | Q1 M1: Approved; Q1 M3: Variance; Q2 M5: Comments
|  |  | 19201.65 | Q1 M1: 39830; Q1 M3: 31.11%
Section 4. Co-funding. Mandatory for agreements above USD 300,000
No. | Cost Grouping | Performance Area | Description of funding support | Q1 M2: Budget (in USD/EUR); Q2 M4: Source of financing; Q3 M8: Comment
1 | External Professional Services | Oversight | Asistencia Tecnica para comité de propuestas. | Q1 M2: 5000; Q2 M4: ONUSIDA; Q3 M8: Apoyar al comité de propuesta en la elaboracion de SF de VIH
2 | bar: Q3 M8 to Q4 M12
3 | bar: Q3 M8 to Q4 M12
4 | bar: Q3 M8 to Q4 M12
5 | bar: Q3 M8 to Q4 M12
5000
Version June 2020
Note on G36: Variance against the total budget.

## ExpenditureCashBce_Year_N
CCM FUNDING AGREEMENT EXPENDITURE AND CASH BALANCE REPORT
Section 1. General Information
CCM Name: |  | CCM El Salvador |  |  | Year of Agreement: |  | Year 1
CCM Agreement No: |  | SLV-CFUND-2008 |  |  | Year Starting Date: |  | 2020-01-01
Agreement Starting Date: |  | 2020-01-01 |  |  | Year Envelope |  | 1
|  | BUDGET |  | EXPENDITURE | CURRENCY | ABSORPTION
GRAND TOTAL (Fixed Costs + Activities) = |  | 120000 |  | 71859.33 |  | 59.88%
Section 2. Fixed costs and HR positions covered by CCM Funding Agreement
2A. Fixed Costs
No. | Cost Grouping | Performance Area | Description | Budget Approved | Expenditure | Expenditure rate | Reasons for Variance
1 | Human Resources | Operations | Human Resources (Secretariat staffs) | 60682.05 | 46678.5 | 76.92% | En esta línea se refleja un remanente de $14,003.55 el cual corresponde a salarios del mes de noviembre y diciembre. El saldo estimado al 31 de diciembre es de $0.00 |  | 2.1
2 | Indirect and Overhead Costs | Operations | Office rental and supplies | 500 | 0 | 0% | En esta línea se refleja un remanente de $500.00 Se ha programado una compra de $200.00 la cual se refleja en el cuadro de compromisos. El saldo estimado al 31 de diciembre es de $300.00 |  | 2.2
3 | Indirect and Overhead Costs | Operations | Office rental and supplies | 15793 | 11349.81 | 71.87% | Esta linea refleja un remanente de $4,443.19. Se tienen compromisos pendientes por la suma de $3,641.55. El saldo estimado al 31 de diciembre es de $801.64 |  | 2.3
4 | Non-health Equipment | Operations | Office Equipement | 2200 | 1052.88 | 47.86% | En esta linea se refleja un remanante de $1,147.12. La compra de las 4 tablets para monitoreo se presupuesto por $550 por cada una incluyendo datos y el precio de compra fue de $263.22 sin servicio de datos. Se estima un compromiso por $6,650. El saldo estimado al 31 de diciembre es de ($5,502.88) |  | 2.4
5 | Indirect and Overhead Costs | Operations | Overhead cost - itemized fees to manage CCM funding (including audit) | 4500 | 3375 | 75% | En esta linea se refleja un remanente de $1,125. Se tienen compromisos de pago para los meses de oct, nov y dic 2020 por $375.00 mensual. El saldo estimado al 31 de diciembre es de $0.00 |  | 2.5
|  |  | Total | 83675.05 | 62456.19 | 74.64% | compromisos | saldo estimado 31 dic
[6 empty] | 21218.86 | 25620.1 | -4401.24
2B. HR positions covered by this agreement. Maximum 2 Full time equivalent positions.
No. | Description | Approved | Reported | Reasons for Variance
1 | Executive Secretary | 1 | 1
2 | Administrative Assistant | 1 | 1
3
4
5
| Total | 2 | 2
Section 3. CCM Activities
3A. Costed Work Plan
No. | Cost Grouping | Performance Area | Activities | Budget approved | Expenditure | Expenditure rate | Reasons for Variance
1 | Travel-related Costs | Oversight | CCM Plenary / General Assembly meeting | 3078 | 1237.07 | 40.19% | Se han cumplido las metas establecidas en esta linea. Se refleja un remanente de $1,840.93 debido a la restricción por cuarentena no se han realizado actividades presenciales de marzo a septiembre. Se cuenta con compromisos por un monto de $1,800. El saldo estimado al 31 de diciembre es de $40.93 |  | 1.1
2 | Travel-related Costs | Oversight | Oversight Committee meetings | 3078 | 553.5 | 17.98% | Las metas establecidas se han cumplido. hay un remanente de $2,524.50 según se explica en la linea anterior. El saldo estimado al 31 de diciembre es de $2,524.50 |  | 1.2
3 | Travel-related Costs | Oversight | Technical Working groups meetings | 2280 | 218.67 | 9.591% | Las metas establecidas se cumplieron, se refleja un remanente de $2,061.33, Se detallan en cuadro anexo compromisos por un monto de $1,000. El saldo estimado al 31 de diciembre es de $1,061.33 |  | 1.3
4 | Travel-related Costs | Oversight | Technical Working groups meetings | 1216 | 1087.13 | 89.4% | Se realizaron las metas segun programa. Se refleja un remanente de $128.87. Se cuenta con compromisos por un monto de $85. El saldo estimado al 31 de diciembre es de $43.87 |  | 1.4
5 | Travel-related Costs | Constituency Engagement | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | 3750 | 540 | 14.4% | En esta línea se refleja un remanente de $3,210, debido a la restricción por cuarentena no se han podido realizar actividades presenciales de marzo a septiembre. Se cuenta con compromisos por un monto de $795.00. El saldo estimado al 31 de diciembre es de $2,415.00 |  | 1.5
6 | Travel-related Costs | Oversight | Site Visits / Monitoring Visits | 2722.95 | 507.21 | 18.63% | Las metas se han cumplido en su mayoria de manera virtual. Se refleja un remanente de $2,215.74. Se cuenta con compromisos por un monto de $400. El saldo estimado al 31 de diciembre es de $1,815.74 |  | 1.6
7 | Travel-related Costs | Constituency Engagement | Constituency engagement meetings (specify in comments) | 5000 | 0 | 0% | En esta línea se refleja un remanente de $5,000, debido a la restricción por cuarentena no se han podido realizar actividades presenciales de marzo a septiembre. Se cuenta con compromisos por un monto de $1,900. El saldo estimado al 31 de diciembre es de $3,100 |  | 1.7
8 | Travel-related Costs | Oversight | Workhops, Meetings and Training | 2500 | 2250 | 90% | la meta establecida se cumplio. A la fecha del reporte se refleja un remanente de $250.00. Hay compromisos por un monto de $170.00. El saldo estimado al 31 de diciembre será de $80.00 |  | 1.8
9 | Travel-related Costs | Oversight | Annual CCM retreat | 4500 | 208.25 | 4.628% | Esta actividad esta programada a desarrollarse en el mes de noviembre. El remanente en esta linea es de $4291.75 al ciere de este informe. Los compromisos son por un monto de $3,460.25 que se utilizaran para esta actividad. El saldo estimado al 31 de diciembre es de $831.50 |  | 1.9
10 | Travel-related Costs | Oversight | Others (Please specify in comments) | 3200 | 2325 | 72.66% | Se cumplieron las metas establecidas. A la fecha del informe se tiene un remanente de $875.00. Se tiene compromisso por $800.00 los cuales serán utilizados según el detalle de compromisos de noviembre y diciembre. El saldo estimado al 31 de diciembre es de $75.00 |  | 1.10.
11 | Travel-related Costs | Constituency Engagement | Technical Working groups meetings | 5000 | 476.31 | 9.526% | Al 30 de Oct el saldo es de $4523.69. Durante los meses de Nov. y Dic se llevarán a cabo actividades presenciales para la preparacion de SF de VIH y TB con un costoaproximado $4,500. El saldo estimado al 31 de diciembre es de $23.69 |  | 1.11.
|  |  | Total | 36324.95 | 9403.14 | 25.89% | compromisos | saldo estimado al 31 de dic
[6 empty] | 26921.81 | 14910.25 | 12011.56
3B. Investment on Civil society engagement (15% of the budget) |  |  | Minimum expected | Approved | Reported | Variance | Reasons for Variance
|  |  | 18011 | 36324.95 | 9403.14 | 25.89% | Al 31 de diciembre se espera haber ejecutado el 69% del presupuesto aprobado ($25,243.14), las razones han sido explicadas en las filas anteriores. Sin emgargo la contrapartida gestionada supera lo programado $6,822.00, para un total de ejecucion del 88% (32,065.14)
Section 4. Co-funding. Please include all additional support for CCM including staff.
No. | Cost Grouping | Performance Area | Description of funding support and source of financing |  | Expenses | Comment
1 | Travel-related Costs | Oversight | Apoyo con movilización en visitas de monitoreo del MCP-ES |  | 300 | MINSAL
2 | External Professional Services | Constituency Engagement | Licencias adicionales para la formación de miembros en el codigod de etica del MCP-ES |  | 680 | IBC SA DE CV
3 | Travel-related Costs | Oversight | Apoyo con local en el desarrollo de reuniones del comité de propuestas |  | 150 | ONUSIDA
4 | Travel-related Costs | Constituency Engagement | EPP para miembros de sociedad civil del MCP-ES en apoyo a la emergencia COVID19 |  | 192 | ONUSIDA
5 | External Professional Services | Constituency Engagement | Asistencia Técnica para la elaboracion de solicitud de fondos VIH 2022-2024 |  | 5000 | ONUSIDA
6 | Communication Material and Publications | Oversight | Apoyo con proyector para sesiones de comites. |  | 500 | ENTREAMIGOS
|  |  |  | Total | 6822
Section 6. Cash Reconciliation
Cash Outflow |  |  |  |  | Reported |  | Comments
Income |  | 1.1 | Cash Balance at the beginning of the period |  | 12086.85 |  | Saldo de proyecto SLV-CFUND-1707
|  | 1.2 | Disbursement from the Global Fund |  | 120000 |  | Primer desembolso de proyecto SLV-CFUND-2008
Cash Outflow |  | 2.1 | Activities |  | -9403.14
|  | 2.2 | Fixed costs |  | -62456.19
Commitments |  | 3.1 | Unpaid invoices, legal obligations, other obligations. |  | 0 |  | El formato da error en esta fila (El dato para esta fila es $40,530.35 por compromisos)
|  |  | Total |  | 60227.52 |  | Este dato no es correcto según explicado en fila anterior
[5 empty] | 19697.17 |  | Debido al error en formato de la fila G70 colocamos el dato correcto en esta fila
Bank information |  | Reported | Comments
Cash Balance as per bank statements |  | 60227.52 | Disponible en cuenta bancaria al cierre del periodo reportado
Cash in transit for the reporting period |  | 0 | Pagos en tránsito que corresponden a gastos del período reportado
Cash in transit after the current reporting period |  | -40530.35 | Compromisos penndientes al cierre del año en ejecución
Total |  | 19697.17
|  | BANK INFORMATION |  |  | CASH RECONCILIATION
|  | 60227.52 | saldo en bancos según SISCA |  | 12087 | Saldo inicial remante de proyectoSLV-CFUND-1707
|  | 40530.35 | compromisos |  | 120000 | Desembolso 2020 proyecto SLV-CFUND-2008
|  | 19697.17 | saldo al 31 dic |  | -9403 | gasto act 1
[5 empty] | -62456 | gasto act 2
[5 empty] | -40530.35 | compromisos
[5 empty] | 19697.65 | saldo al 31 dic
[5 empty] | 7610.32 | Saldo real de presupuesto de proyecto SLV-CFUND-2008
Note on D67: Cash balance including commitments. Please specify the amount of commitments in the "Comments" section

## Compromisos y Act.Ptes
COMPROMISOS MCP-ES OCT- DIC 2020
N° | CONCEPTO | LINEA | FECHA | PROVEEDOR | MONTO | COMENTARIOS
O C T U B R E 2020
ACTIVIDAD 1
1 | Pago por 1 licencia adicional Curso Virtual de Etica | 1.4 | 2020-10-30 | IBC SA DE CV | 85
2 | Pago por 2 licencias adicionales Curso Virtual de Etica | 1.8 | 2020-10-30 | IBC SA DE CV | 170
3 | Actualización de pagina web octubre 2020 | 1.10. | 2020-10-30 | SOCIALINK | 200
| TOTAL ACTIVIDAD 1 |  |  |  | 455
ACTIVIDAD 2
4 | pago de alquiler SISCA oct 2020 | 2.3 | 2020-12-15 | SISCA | 1110
5 | Pago de lineas móviles oct 2020 | 2.3 | 2020-12-15 | CLARO EL SALVADOR | 103.85
6 | Pago de Overhead SISCA oct 2020 | 2.5 | 2020-12-15 | SISCA | 375
| TOTAL ACTIVIDAD 2 |  |  |  | 1588.85
TOTAL OCTUBRE 2020 |  |  |  |  | 2043.85
N O V I E M B R E 2020
ACTIVIDAD 1
7 | Sesion plenaria ME07-2020 | 1.2 | pte | Hotel Alicante | 0 | Se eliminó la cantidad $700.00
8 | Sesiones comité ejecutivo ampliado para el mes de noviembre | 1.3 | pte | pte | 500 | Debido al proceso de elaboración de las propuestas se espera realizar mas reuniones del comité adhoc para la selección del RP, las cuales serian cargadas a esta línea
9 | Gastos por movilización actividades del mes nov | 1.5 | 2020-11-30 | Planilla de miembros | 295 | Solicitud de anticipo aprobada
10 | Elaboración de informes de visitas de campo 07 y 08 | 1.6 | 2020-11-30 | ADELAIDA OSORIO | 400
11 | Retiro Anual de Miembros | 1.9 | 18 y 19 nov | Hotel Alicante, Multipromociones, Ciriaco SV, Luis Beltran y otros | 3460.25 | Gastos ya realizados
12 | Actualización de pagina web noviembre 2020 | 1.10. | 2020-11-30 | SOCIALINK | 200
13 | Reuniones del Comité de propuestas 04 nov | 1.11 | 2020-11-04 | Hotel Marriot | 200
14 | Reuniones del Comité de propuestas 12 y 13 nov | 1.11 | 12 y 13 nov | Circulo Militar | 800
15 | Reuniones del Comité de propuestas 16 nov | 1.11 | 2020-11-16 | Hotel Marriot | 600
16 | Diseño grafico de llamado público para selección RP | 1.11 | pte | REBECA AYALA | 75 | Este será utilizado para publicar en web y redes sociales
17 | Reuniones del Comité de propuestas nov | 1.11 | pte | Pendiente | 1375 | Se espera realizar mas reuniones por motivo del proceso de elaboración de las propuestas VIH y TB
TOTAL ACT 1 |  |  |  |  | 7905.25
ACTIVIDAD 2
18 | Pago de salarios staff nov 2020 | 2.1 | 2020-11-20 | Staff | 4667.85
19 | pago de alquiler SISCA nov 2020 | 2.3 | 2020-11-20 | SISCA | 1110
20 | Pago de lineas móviles nov 2020 | 2.3 | 2020-11-20 | CLARO EL SALVADOR | 103.85
21 | Compra de audifonos, mouse y otros | 2.2 | nov | Office depot y Claro | 200
22 | Pago de Overhead SISCA nov2020 | 2.5 | 2020-11-20 | SISCA | 375
TOTAL ACT 2 |  |  |  |  | 6456.7
TOTAL NOVIEMBRE 2020 |  |  |  |  | 14361.95
D I C I E M B R E 2020
ACTIVIDAD 1
23 | Asamblea Plenaria 08-2020 | 1.1 | 2020-12-03 | CAJAMARCA | 1000 | local y alimentación para 25 miembros jornada completa
24 | Compra de insumos para plenaria 08-2020 | 1.1 | 2020-12-03 | Pricesmart y otros | 300 | Insumos de ambientación para salón en plenaria 08
25 | Asambleas extraordinarias por aprobacion de avances de sol de fondos 2022-2024 | 1.1 | dic | pte | 500 | Dependera de reprogramaciones por el proceso de selección de RP y avances con la SF
26 | Sesiones comité ejecutivo ampliado dic | 1.3 | pte | pte | 500 | Debido al proceso de elaboración de las propuestas se espera realizar mas reuniones del comité adhoc para la selección del RP, las cuales serian cargadas a esta línea
27 | Gastos por movilización actividades del mes dic | 1.5 | 2020-12-03 | Planilla de miembros | 350
28 | Pago por movilizacion de miembros en plenaria 08 | 1.5 | 2020-12-03 | PABLITOS TOURS | 150 | movilizacion de San Salvador a Cajamarca
29 | Pago por sistematizacion de dialogos de pais | 1.7 | 2020-12-10 | pte | 1500 | Asistencia tecnica para la sistematización de los dialogos de pais
30 | Pago por luces LED para evento en el marco del 1 dic | 1.7 | 2020-12-03 | pte | 400
31 | Actualización de pagina web diciembre 2020 | 1.10. | 2020-12-10 | SOCIALINK | 200
32 | Diagramación de boletin correspondiente al Q4 | 1.10. | 2020-12-10 | REBECA AYALA | 200
33 | Reuniones del Comité de propuestas diciembre | 1.11 | 2020-12-15 | pte | 1450 | Se espera realizar mas reuniones por motivo del proceso de elaboración de las propuestas VIH y TB
TOTAL ACT 1 |  |  |  |  | 6550
ACTIVIDAD 2
34 | Pago de salarios staff | 2.1 | 2020-12-15 | Staff | 9335.7
35 | pago de alquiler SISCA | 2.3 | 2020-12-15 | SISCA | 1110
36 | Pago de lineas móviles | 2.3 | 2020-12-15 | CLARO EL SALVADOR | 103.85
37 | Pago de Overhead SISCA dic 2020 | 2.5 | 2020-12-15 | SISCA | 375
38 | Compra de Laptop para especialista de monitoreo con accesorios | 2.4 | 2020-12-15 | pendiente | 3500
39 | Licencias de office, antivirus, CAL, Adobe para nuevo equipo | 2.4 | 2020-12-15 | pendiente | 400
40 | Compra de equipo para conferencia | 2.4 | 2020-12-15 | pendiente | 2500
41 | Compra de 5 modem inalambrico corporativo | 2.4 | 2020-12-15 | pendiente | 250
TOTAL ACT 2 |  |  |  |  | 17574.55
TOTAL DICIEMBRE 2020 |  |  |  |  | 24124.55
TOTAL COMPROMISOS |  |  |  |  | 40530.35

## List
Cost Grouping | CCM Secretariat positions | Activities | Fixed Costs Activities
Human Resources | Executive Secretary | Annual CCM retreat | Human Resources (Secretariat staffs)
Indirect and Overhead Costs | Administrative Assistant | CCM Board meeting | Office rental and supplies
Non-health Equipment | Oversight Officer | CCM Elections | Office Equipement
External Professional Services | Finance Officer | CCM Induction / Orientation | Vehicule maintenance
Communication Material and Publications |  | CCM Plenary / General Assembly meeting | Overhead cost - itemized fees to manage CCM funding (including audit)
Travel-related Costs |  | Constituency consultations for non-governmental constituencies only and processes to promote and improve the quality of stakeholder participation. | Others (Please specify in comments)
Constituency engagement meetings (specify in comments)
|  | Others (Please specify in comments) | Performance Area
|  | Oversight Committee meetings | Operations
Year | Currency | Site Visits / Monitoring Visits | Oversight
Year 1 | USD | Technical Support | Constituency Engagement
Year 2 | EUR | Technical Working groups meetings | Sustainability, Transition and Linkages
Year 3 |  | Workhops, Meetings and Training
Year 4 (Exceptionnal) |  | Workshops, Meetings for Funding Request development
Workshops, Meetings for Grant Making
Assessment outcome | Yes/No | Workshops, Meetings for Reprogramming
Exceptional | Yes
Performing well | No
A few minor issues
Serious Issues

## CCMRCM (hidden)
CCM Afghanistan
CCM Albania
CCM Algeria
CCM Angola
CCM Armenia
CCM Azerbaijan
CCM Bangladesh
CCM Belarus
CCM Belize
CCM Benin
CCM Bhutan
CCM Bolivia
CCM Bosnia and Herzegovina
CCM Botswana
CCM Bulgaria
CCM Burkina Faso
CCM Burundi
CCM Cambodia
CCM Cameroon
CCM Central African Republic
CCM Chad
CCM Colombia
CCM Comoros
CCM Congo (Democratic Republic)
CCM Congo (Republic of)
CCM Costa Rica
CCM Cote d'Ivoire
CCM Cuba
CCM Djibouti
CCM Dominican Republic
CCM Ecuador
CCM El Salvador
CCM Eritrea
CCM Ethiopia
CCM Fiji
CCM Gabon
CCM Gambia
CCM Georgia
CCM Ghana
CCM Guatemala
CCM Guinea
CCM Guinea-Bissau
CCM Guyana
CCM Haiti
CCM Honduras
CCM India
CCM Indonesia
CCM Iran (Islamic Republic of)
CCM Jamaica
CCM Kazakhstan
CCM Kenya
CCM Kosovo
CCM Kyrgyzstan
CCM Lao PDR
CCM Lesotho
CCM Liberia
CCM Macedonia
CCM Madagascar
CCM Malawi
CCM Malaysia
CCM Mali
CCM Mauritania
CCM Mauritius
CCM Moldova
CCM Mongolia
CCM Montenegro
CCM Morocco
CCM Mozambique
CCM Myanmar
CCM Namibia
CCM Nepal
CCM Nicaragua
CCM Niger
CCM Nigeria
CCM Pakistan
CCM Panama
CCM Papua New Guinea
CCM Paraguay
CCM Peru
CCM Philippines
CCM Romania
CCM Russian Federation
CCM Rwanda
CCM São Tomé and Príncipe
CCM Senegal
CCM Sierra Leone
CCM Solomon Islands
CCM South Africa
CCM South Sudan
CCM Sri Lanka
CCM Sudan
CCM Suriname
CCM Swaziland
CCM Tajikistan
CCM Tanzania
CCM Thailand
CCM Timor Leste
CCM Togo
CCM Tunisia
CCM Uganda
CCM Ukraine
CCM Uzbekistan
CCM Viet Nam
CCM Zambia
CCM Zanzibar
CCM Zimbabwe
Non-CCM Somalia
RCM Abidjan-Lagos Corridor Organisation
RCM African Regional Coordinating Mechanism
RCM Asia (Regional Steering Committee)
RCM EMMIE (Mesoamerica)
RCM Organisation of Eastern Caribbean States
RCM Pan Caribbean Partnership against HIV/AIDS
RCM Regional Coordinating Mechanism for the Regional Response to TB in the mining sector in Southern Africa
RCM Western Pacific
RO Comite Asesor Regional para subvenciones del Fondo Mundial en America Latina y el Caribe – CAR LAC